## Sheet1
Risk	Description	Category	Triggers	Root cause	Potential responses	Risk Owner	Probability ( high 5, low 1 )	Impact ( high 5, low 1 )	Score
ANN does not work	the back propagation algorithm / Is not working as expected.	Software	improper behaviour / of the program output	Inability to understand and / properly implement the back / Propagation algorithm.	Re-design or fix the / back-propagation / algorithm	Developer	4	5	20
API does not work	The Application interface does / Not working as expected	Software	improper behaviour of / The IO interface	bugs in the API code and / Horribly designed interface	Tweak the interface / Module to fix bugs	Developer	3	3	9
ANN takes too long / To adjust weights	The neural network training / Process is taking too long / to adjust the synaptic weights	Software/ / Hardware	Penalises productivity / And efficiency for the / Medical expert	low computational power, / No optimization whatsoever	Re-design the bottlenecks / And optimize the process / Of the back-prop algorithm	Developer/ / User	1	2	2
Non-existent GSL lib	The host computer does not / Have the GNU scientific library / Installed locally.	Software/ / Hardware/ / User	Inability to compile and / Execute the aplication	User did not install project / Dependencies	Install the GNU scientific / Library and re-compile	User	4	3	12
Horrible user-interface	The user interface is so complicated / Or confusing that the user is unable / To query for a classification result	Design/ / Software	Inability to run the / Application program	Not properly taking into / Consideration usability / Engineering principles	Re-design the user-interface / And accept user feed-back	Developer	4	4	16